## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | PROJECT MEMBER | PROJECT MEMBER
Creating a data visualization dashboard for monitoring key metrics and performance indicators in a manufacturing plant. | Qingyuan Hu | Yunmu Shu
PROJECT DELIVERABLE | Datasets collection. Data cleaning, preprocessing, and structuring. Backend design. | Dashboard integration and frontend design. API setup and interactivity.
SCOPE STATEMENT
START DATE | END DATE | OVERALL PROGRESS
2025-05-19 | 2025-08-11 | 25%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Team Formation and Topic Description | Qingyuan Hu, Yunmu Shu | 2025-05-19 | 2025-06-02 | 14 | Complete
Iteration #02 | Qingyuan Hu, Yunmu Shu | 2025-06-02 | 2025-06-09 | 7 | Complete
Define metrics and find datasets | Qingyuan Hu | 2025-06-09 | 2025-06-16 | 7 | Complete
Data cleaning and preprocessing | Qingyuan Hu | 2025-06-16 | 2025-06-23 | 7 | In Progress
Provide interfaces for front/back ends | Qingyuan Hu | 2025-06-23 | 2025-06-30 | 7 | In Progress
Develop visualizations | Yunmu Shu | 2025-06-30 | 2025-07-07 | 7 | Not Started
Develop dashboard wireframes | Yunmu Shu | 2025-07-07 | 2025-07-14 | 7 | Not Started
Final dashboard prototype with interactivity | Yunmu Shu | 2025-07-14 | 2025-07-21 | 7 | Not Started
Debug and evaluation | Qingyuan Hu, Yunmu Shu | 2025-07-21 | 2025-07-28 | 7 | Not Started
Final submission with report and documentation | Qingyuan Hu, Yunmu Shu | 2025-07-28 | 2025-08-04 | 7 | Not Started
Prepare for presentation | Qingyuan Hu, Yunmu Shu | 2025-08-04 | 2025-08-11 | 7 | Not Started